## Slide 1: Paramedics and CMC
Kate Kandasamy July 2021
Using the wider Healthcare Team to deliver ACP conversations

## Slide 2
Wandsworth created over 2000 CMC records over Wave 1
Some uncertainty about quality - particularly patient wishes, contact details and Treatment escalation plans
PCN debriefs after Wave 1 highlighted issues around sustainability
Expansion of Additional Roles in PCNs already happening and increasing in 2022
How could we encourage a broader approach to having ACP conversations?

## Slide 3
Could using Paramedics be a solution?

## Slide 4
Already independent Practitioners
Already providing both acute and chronic home visiting services
Probably already seeing patients we might not be identifying
Experience of using CMC in an emergency so good insight into what is helpful
More time than GPs

## Slide 5
What has gone well?

## Slide 6
Successful recuited an experienced Paramedic
Identified and engaged with a PCN to host the Paramedic
Training and Supervision organised
Rolled out Early Identification Toolkit across the PCN
To date 30 new CMC records created
Upskilling of other staff members within the PCN

## Slide 7
What have we learned?

## Slide 8
Very positive feedback from Patients and Families
Very positive feedback from GPs and Staff
Increased awareness of ACP conversations within the PCN
High engagement with my CMC - >90%
It takes time - most records required 2 visits
Supervision, training and connections all take time
Logistics - IT set up, Parking! Resource allocation across Practices

## Slide 9
What next?

## Slide 10
Formal end of project assessment
  Quality, Patient and PCN feedback
Roll out to other PCNs - initially planned for September
Engagement with adjacent Borough
Training plan to link with Paramedic Roadmap