## Project Plan
SIM London | [10 empty] | Today
Project Plan to Implement SIM 136 Model - Joint | [10 empty] | 2018-06-08
2018
[15 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Ref | Stage | Task | Owner | Milestone | Start | End | Status - Trust 1 | Status - Trust 2 | Status - Trust 3 | Status - Trust 4 | Days overdue - Trust 1 | Days overdue - Trust 2 | Days overdue - Trust 3 | Days overdue - Trust 4 | time axis 2018-03-05 to 2018-09-28
1 | Step 1 - Presentation and Business Case | [9 empty] | #N/A | #N/A |  | #N/A
1.01 | Step 1 | Attend SIM presentation | Project Sponsor | [7 empty] | #N/A | #N/A |  | #N/A
1.02 | Step 1 | Identify project lead | Project Sponsor | M | [6 empty] | #N/A | #N/A | #N/A | #N/A
1.03 | Step 1 | Join High Intensity Network | All | [7 empty] | #N/A | #N/A | #N/A | #N/A
1.04 | Step 1 | Identify funding source | Project Lead | M | [6 empty] | #N/A | #N/A | #N/A | #N/A
1.05 | Step 1 | Adapt High Intensity Network business case | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
1.06 | Step 1 | Present business case to secure funding | Project Sponsor | M | [6 empty] | #N/A | #N/A | #N/A | #N/A
1.07 | Step 1 | Identify key partners/stakeholders/service users | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
1.08 | Step 1 | Communicate funding outcome to stakeholders | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
1.09 | Step 1 | Memorandum of Understanding signed and returned | Project Sponsor | [7 empty] | #N/A | #N/A | #N/A | #N/A
1.1 | Step 1 | Identify project team | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
1.11 | Step 1 | Include service user and carer representatives in project team | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
1.12 | Step 1 | Identify and include ED contact on project team | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
1.13 | Step 1 | Include lead AMHP on project team | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
1.14 | Step 1 | Invite local Authority Rep to project team | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
1.15 | Step 1 | Include Comms lead on project team | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
2 | Step 2 - Project Design | [9 empty] | #N/A | #N/A | #N/A | #N/A
2.01 | Step 2 | Download the Operational Delivery Guide template | Project Manager | [7 empty] | #N/A | #N/A | #N/A | #N/A
2.02 | Step 2 | Team name chosen and sent to Paul | All | [7 empty] | #N/A | #N/A | #N/A | #N/A
2.03 | Step 2 | Complete High Intensity 1 day Training - Briefing | All | M | [6 empty] | #N/A | #N/A | #N/A | #N/A
2.04 | Step 2 | Arrange local team meetings | Project Manager | [7 empty] | #N/A | #N/A | #N/A | #N/A
2.05 | Step 2 | Identify S136 high intensity users | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
2.06 | Step 2 | Operational Guide edited to fit local policy and procedure | Project Manager | [7 empty] | #N/A | #N/A | #N/A | #N/A
2.07 | Step 2 | Agree data collection & reporting | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
2.08 | Step 2 | Communicate with stakeholders (including service users) about the project | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
2.09 | Step 2 | Agree Local SIM board and set up ongoing meetings | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
3 | Step 3 - Information Governance | [9 empty] | #N/A | #N/A | #N/A | #N/A
3.01 | Step 3 | Review section 9 of operational delivery guide | Project Manager | [7 empty] | #N/A | #N/A | #N/A | #N/A
3.02 | Step 3 | Meet with Caldicott Guardian | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
3.03 | Step 3 | Complete Privacy Impact Assessment | Project Manager | [7 empty] | #N/A | #N/A | #N/A | #N/A
3.04 | Step 3 | Complete Equality Impact Assessment | Project Manager | [7 empty] | #N/A | #N/A | #N/A | #N/A
3.05 | Step 3 | Agree parties to sharing framework | Project Lead | M | [6 empty] | #N/A | #N/A | #N/A | #N/A
3.06 | Step 3 | Sign off sharing data framework | Project Lead | M | [6 empty] | #N/A | #N/A | #N/A | #N/A
3.07 | Step 3 | Identify organisational IG lead | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
3.08 | Step 3 | Communicate with stakeholders (including service users) about IG | Project Manager | [7 empty] | #N/A | #N/A | #N/A | #N/A
3.09 | Step 3 | Review service user leaflet and localise if necessary | Project Manager | [7 empty] | #N/A | #N/A | #N/A | #N/A
4 | Step 4 - Network Data | [9 empty] | #N/A | #N/A | #N/A | #N/A
4.01 | Step 4 | Review the Project Data Guide | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
4.02 | Step 4 | Download national data templates | Project Manager | [7 empty] | #N/A | #N/A | #N/A | #N/A
4.03 | Step 4 | Responsible lead to input national data | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
4.04 | Step 4 | Identify Community Mental Health Team (CMHT) | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
4.05 | Step 4 | Calculate 5 local cost figures | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
4.06 | Step 4 | Collate data on high intensity cases | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
5 | Step 5 - Plan the Launch | [9 empty] | #N/A | #N/A | #N/A | #N/A
5.01 | Step 5 | Identify launch date (Monday) | All | [7 empty] | #N/A | #N/A | #N/A | #N/A
5.02 | Step 5 | Book Paul Jennings for training week (week prior to launch date) | AHSN | [7 empty] | #N/A | #N/A | #N/A | #N/A
5.03 | Step 5 | Plan launch event (if required) | AHSN
6 | Step 6 - Select Teams (and service users) | [9 empty] | #N/A | #N/A | #N/A | #N/A
6.01 | Step 6 | Advertise expression of interest for SIM Officer | Police | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.02 | Step 6 | Agree job specification | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.03 | Step 6 | Advertise SIM officer | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.04 | Step 6 | Design interview questions/format | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.05 | Step 6 | Joint Interview | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.06 | Step 6 | Confirm successful candidate | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.07 | Step 6 | Agree first cohort of service users | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.08 | Step 6 | Select Care Co-ordinators | CMHT Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.09 | Step 6 | Audit Care records and ensure up to date | CMHT Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.1 | Step 6 | Set up procedure to support and debrief staff impacted incase of Serious Incident | CMHT Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.11 | Step 6 | Identify NHS line manager | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.12 | Step 6 | Identify NHS clinical supervisor | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.13 | Step 6 | NHS Honorary contract signed | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
6.14 | Step 6 | Arrange ID & laptop - office induction for Police officer | CMHT Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
7 | Step 7 - Brief Teams | [9 empty] | #N/A | #N/A | #N/A | #N/A
7.01 | Step 7 | Communicate with stakeholders about project progress | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
7.02 | Step 7 | Select and brief CMHT team | CMHT Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
7.03 | Step 7 | Identify single point of contact/lead investigator for the project | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
7.04 | Step 7 | Launch Celebration Event (if required) | AHSN | [7 empty] | #N/A | #N/A | #N/A | #N/A
8 | Step 8 - Train | [9 empty] | #N/A | #N/A | #N/A | #N/A
8.01 | Step 8 | Book Venue for SIM 1-week training | AHSN
8.02 | Step 8 | NHS Induction | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
8.03 | Step 8 | Complete SIM 1 week training | All | [7 empty] | #N/A | #N/A | #N/A | #N/A
8.04 | Step 8 | Communicate launch to CCG, MH trust, Police, LAS, ED, family's & Service users | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
8.05 | Step 8 | Launch Day | All | [7 empty] | #N/A | #N/A | #N/A | #N/A
9 | Step 9 - Connect | [9 empty] | #N/A | #N/A | #N/A | #N/A
9.01 | Step 9 | Request training portal log in | Project Lead | M | [6 empty] | #N/A | #N/A | #N/A | #N/A
9.02 | Step 9 | Post Launch monitoring and evaluation | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
9.03 | Step 9 | Ongoing communication | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
9.04 | Step 9 | Contribute to and utilise the High Intensity Network | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
9.05 | Step 9 | Ongoing support | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
9.06 | Step 9 | Calculate Finance-Funding-Savings | Project Lead | [7 empty] | #N/A | #N/A | #N/A | #N/A
[11 empty] | #N/A | #N/A | #N/A | #N/A
Note on Q7: Josh Brewster: Add Start Date here

## Project Team
SIM London
Project Team
Initial Core Team
Project team | Trust 1 | Trust 2 | Trust 3 | Trust 4 | Key responsibilities
Project lead
Communications Lead
IG Lead
Informatics Lead
Data Contact
Finance lead
CCG lead
CMHT lead
Police Lead (SPOC)
AMHP Lead
Ambulance Service lead
Acute trust ED lead
Service user representation
Family/carer representation
Local Authority Representative
Members that will be added as project progresses
Care Coordinators
Care Coordinators
Police Officer
Additional Members that you may wish to add
Project Manager/Support
IT Lead
Public Health Lead
Lead Consultant
Consultant Psychologist
Head of Volunteering Services
Divisional Director for Community Services

## Risk & Issue Log
SIM London
Risk Register and Issue Log
Ref | Type | Description | Mitigation (planned) | Mitigation (actioned) | Comments | Organisation | Date entered | Date updated | Date Closed | Score (risk) |  |  | Score (issue)
[10 empty] | L | C
R.001 | Risk | Example risk | Example risk - action planned to mitigate | Example risk -action taken to mitigate | [7 empty] | 0
I.001 | Issue | Example issue | Example issue - action planned to mitigate | Example issue -action taken to mitigate | [7 empty] | 0
RI.001 | Risk | [10 empty] | 0
RI.002 | Risk | [10 empty] | 0
RI.003 | Risk | [10 empty] | 0
RI.007 | Risk | [10 empty] | 0
RI.008 | Risk
RI.009 | Risk
RI.010 | Risk
RI.011 | Risk
RI.012 | Risk | [10 empty] | 0
RI.013 | Risk | [10 empty] | 0
RI.014 | Risk | [10 empty] | 0
RI.015 | [11 empty] | 0
RI.016 | [11 empty] | 0
RI.017 | [11 empty] | 0
RI.018 | [11 empty] | 0
RI.019 | [11 empty] | 0
RI.020 | [11 empty] | 0
RI.021 | [11 empty] | 0
RI.022 | [11 empty] | 0
RI.023 | [11 empty] | 0
RI.024 | [11 empty] | 0
RI.025 | [11 empty] | 0
RI.026 | [11 empty] | 0
RI.027 | [11 empty] | 0
RI.028 | [11 empty] | 0
RI.029 | [11 empty] | 0
RI.030 | [11 empty] | 0
RI.031 | [11 empty] | 0
RI.032 | [11 empty] | 0
RI.033 | [11 empty] | 0
RI.034 | [11 empty] | 0
RI.035 | [11 empty] | 0
RI.036 | [11 empty] | 0
RI.037 | [11 empty] | 0
RI.038 | [11 empty] | 0
RI.039 | [11 empty] | 0
RI.040 | [11 empty] | 0

## Lists
Milestone | Status | Risk/Issue | Risk | Issue | Risk matrix | [5 empty] | Org
[5 empty] | 5 | 5 | 10 | 15 | 20 | 25
M | Complete | Risk | 1 | Low | 4 | 4 | 8 | 12 | 16 | 20 | Oxleas
| Incomplete | Issue | 2 | Medium | 3 | 3 | 6 | 9 | 12 | 15 | SLAM
| Overdue |  | 3 | High | 2 | 2 | 4 | 6 | 8 | 10 | CandI
| N/A |  | 4 | V.High | 1 | 1 | 2 | 3 | 4 | 5 | SWLSTG
|  |  | 5 |  |  | 1 | 2 | 3 | 4 | 5 | All
HIN